## Summary
Quoted total (supplier stated €) | Line item calc total €
5400000 | 5400000

## BOM
Item | Description | Unit | Qty | Unit price (EUR) | Line total (EUR)
Base umbilical (per m) | Hybrid umbilical base cable (24F, 6x1/2" super duplex tubes, 3x 6mm² conductors) | m | 2400 | 1750 | 4200000
Terminations & Test Heads | Lump sum for terminations, bend stiffeners, test heads, FAT activities | LS | 1 | 1200000 | 1200000

## PaymentPlan
Milestone | Percent
Advance payment on NTP | 20
FAT completion | 30
Delivery DDP Kristiansund | 40
Final acceptance / documentation close-out | 10
Retention held until final acceptance | 2

## Schedule
Activity | Duration_weeks | Start
Engineering & drawings approval | 12 | ARO
Manufacturing & FAT | 34 | After eng approval
Delivery to Kristiansund | Per schedule | After FAT

## Certs&Docs
Certification | Status | Docs
DNV-ST-F119 | Included
NORSOK Z-001 alignment | Included where applicable
| Included | FAT, MRB, CoC, Coating report, GA, BOM