# OneSubsea (SLB) — Commercial Offer: Hybrid Umbilical 24F 10kpsi

Prepared: 2025-09-19

OneSubsea (SLB) — Commercial Offer: Hybrid Umbilical 24F 10kpsi

Prepared: 2025-09-19

COMMERCIAL PROPOSAL

-------------------

Scope: Supply of 2 × 1.2 km Hybrid Umbilicals (24 single-mode fibers, 8 × 1/2" steel tubes, 2 × electrical twisted pairs).

Pricing (quoted by OneSubsea):

- Unit cost: €1,900 / m (base umbilical)

- Terminations, Bend Stiffeners, Test Heads: €1,350,000 (lump sum)

- Quoted total estimated cost (supplier statement): €5,800,000

- Line-item calculation (unit price × 2,400 m + terminations): €1,900 × 2,400 = €4,560,000 + €1,350,000 = €5,910,000

-> NOTE: Quoted total (€5.8M) differs from the line-item arithmetic (€5.91M). Please confirm which total to use for award and whether any discounts or bundled scope were applied in the quoted total.

Optional bundle discount:

- 8% reduction on the umbilical package if awarded together with SPS/Controls scope (applies to the umbilical base price only unless otherwise agreed).

Commercial terms:

- Pricing basis: DDP Kristiansund Base (Vestbase) — see assumptions for clarifications.

- Validity: 60 days from offer date.

- Retention: 2% held until final acceptance (included in milestone payments).

- Payment terms: Net 30 days from invoice date.

Payment milestone schedule (as provided by OneSubsea / SLB):

- Milestone 1 – Contract award / NTP: 15%

- Milestone 2 – Engineering package & drawings approved (SDRL Gate A): 15%

- Milestone 3 – Long-lead materials received (steel tubes, fibers, armor): 25%

- Milestone 4 – Mechanical completion of both umbilicals (pre-FAT): 20%

- Milestone 5 – FAT completed & DNV witness acceptance; MRB submitted (SDRL Gate F): 15%

- Milestone 6 – Delivery DDP Kristiansund / custody transfer: 8%

- Milestone 7 – Final acceptance / punch-list close-out (30 days after delivery): 2%

DELIVERY & SCHEDULE

-------------------

- Engineering & drawings approval: 14 weeks ARO

- Manufacturing & FAT: 40 weeks

- Delivery at Kristiansund Base: Week 46, 2026 (≈ 13 months ARO)

- High-level schedule notes: schedule assumes timely approvals, raw material availability, access for DNV witness testing, and no force majeure events. Detailed EPS schedule and risk register to be provided upon NTP.

TECHNICAL HIGHLIGHTS & SPECIFICATIONS

-------------------------------------

- Hybrid umbilical configuration: 24 single-mode fibers (SM), 8 × 1/2" steel tubes (10,000 psi rating), 2 × electrical twisted pairs (for controls), fiber optic attenuation ≤0.35 dB/km @ 1310 nm.

- Outer diameter (approx): 124 mm

- Weight in air (approx): 68 kg/m

- Minimum bend radius (approx): 3.2 m

- Construction notes: armor, sheathing, tube welding procedures, and conductor terminations compliant with SLB OneSubsea manufacturing standards.

DOCUMENTATION, TESTS & DELIVERABLES

-----------------------------------

Included documentation and records (delivered with the package):

- GA drawings and detailed cross-sections

- Complete Bill of Materials (BOM)

- Material certificates (EN 10204 3.1 / 3.2) for metallic components

- Factory Acceptance Test (FAT) reports including: hydraulic pressure cycling, fiber OTDR test reports, electrical insulation/IR tests, mechanical tests as per SDRL

- Coating & paint reports, CoC, MRB and Welding Procedure Qualifications (PQs)

- Handling & Installation Manual (HIM) tailored for Kristiansund mobilization

- SDRL alignment: Equinor SDRL / NORSOK Z-001 (as applicable)

- Digital integration: structured BOM and FAT records available via SLB/OneSubsea digital delivery platform (DELFI) where applicable

QUALITY & STANDARDS

-------------------

- Primary qualification: DNV-ST-F119 (Umbilical design & manufacturing)

- Additional standards: API 17E (where applicable for controls/hoses) — OneSubsea states dual compliance (DNV-ST-F119 / API 17E) for relevant subsystems.

TESTING & ACCEPTANCE

--------------------

- FAT: to be performed at OneSubsea designated facility and witnessed by DNV per SDRL. FAT to include: hydrostatic test, pressure cycling, OTDR fiber testing, electrical IR, functional tests on terminations and test heads.

- MRB: Material Review Board documentation and Non-Conformance reporting per contract.

- Witness & inspection: DNV witness attendance included in the FAT milestone (costs assumed included in DDP pricing unless explicitly stated otherwise).

ASSUMPTIONS & EXCLUSIONS (STANDARD)

-----------------------------------

Assumptions (used as the basis for the quoted price):

- Pricing is based on DDP delivery to Kristiansund Base (Vestbase). Confirm whether customs duties and local VAT are included in the DDP pricing; if not included they will be charged separately.

- Supplier to be granted timely access for DNV witness testing and customer FAT reviews at nominated facilities.

- No offshore installation, onshore installation services, third-party lifting, or third-party survey included (priced separately).

- No scope for spare parts beyond standard commissioning spares unless specified.

- Any changes to specifications, materials, or schedule requested after NTP may be subject to re-pricing and will affect delivery dates.

GAP ITEMS / CLARIFICATIONS REQUIRED (ACTION)

-------------------------------------------

1. Confirm whether the quoted supplier total (€5.8M) already includes the 8% bundle discount or alternative discounts — line-item arithmetic indicates €5.91M. Please request supplier confirmation and an updated breakdown if needed.

2. Confirm DDP inclusions (duties, VAT) in writing.

3. Confirm whether early-payment discounts or other commercial concessions were applied when deriving the quoted total.

4. Provide EPS schedule and detailed risk register prior to NTP.

KEY REFERENCES & PAST PROJECTS

------------------------------

- Snorre Expansion Project — subsea controls + umbilicals (SLB / OneSubsea scope examples)

- Åsgard Subsea Compression — high-pressure control umbilicals

- Gulf of Mexico — deepwater SURF systems (global delivery references)

- Additional references available upon request

CONTACT (COMMERCIAL)

--------------------

OneSubsea (SLB) — Commercial Contact (sample)

Email: contact.sales@onesubsea.example

Phone: +47 55 00 00 00

END OF OFFER