## Summary
Quoted total (supplier stated €) | Line item calc total €
5800000 | 5910000

## BOM
Item | Description | Unit | Qty | Unit price (EUR) | Line total (EUR)
Base umbilical (per m) | Hybrid umbilical base cable (24F, 8x1/2" tubes, 2x twisted pairs) | m | 2400 | 1900 | 4560000
Terminations & Test Heads | Lump sum for terminations, bend stiffeners, test heads, FAT activities | LS | 1 | 1350000 | 1350000

## PaymentPlan
Milestone | Percent
Contract award / NTP | 15
Engineering package & drawings approved (SDRL Gate A) | 15
Long-lead materials received | 25
Mechanical completion (pre-FAT) | 20
FAT completed & DNV witness acceptance (SDRL Gate F) | 15
Delivery DDP Kristiansund / custody transfer | 8
Final acceptance / punch-list close-out | 2
Retention held until final acceptance | 2

## Schedule
Activity | Duration_weeks | Start
Engineering & drawings approval | 14 | ARO
Manufacturing & FAT | 40 | After eng approval
Delivery to Kristiansund | Per schedule | After FAT

## Certs&Docs
Certification | Status | Docs
DNV-ST-F119 | Included
API 17E | Included where applicable
| Included | FAT, MRB, CoC, Coating report, GA, BOM