Aker Solutions - Offer (Hybrid Umbilical 24F 10kpsi)

Prepared: 2025-09-19

SUMMARY

-------

Scope: Supply of 2 × 1.2 km hybrid umbilicals (24F, 10kpsi steel-tube hybrid).

Unit cost (base umbilical): €1,750/m

Terminations, Bend Stiffeners, Test Heads (lump sum): €1,200,000

Total estimated cost (2 × 1.2 km): €5,400,000 (breakdown below)

Validity: 60 days from offer date.

Delivery: DDP Kristiansund Base - Week 42, 2026 (~11 months ARO)

Payment terms: 20% advance / 30% after FAT / 40% on delivery / 10% after acceptance

Retention: 2% (included in milestones)

BREAKDOWN (assumptions: 2 umbilicals x 1,200 m = 2,400 m)

- Cable manufacturing (2,400 m × €1,750/m) = €4,200,000

- Terminations & test heads (lump) = €1,200,000

- Subtotal = €5,400,000

Notes: Freight, insurance, duties, and VAT excluded (priced to DDP Kristiansund).

TECHNICAL HIGHLIGHTS

--------------------

- Configuration: 6 × 1/2" super duplex steel tubes (10,000 psi), 24 SM fibers, 3 × 6 mm² Cu conductors

- Outer diameter: 118 mm

- Weight in air: 63 kg/m

- Fiber attenuation: ≤0.35 dB/km @1310 nm

- Min bend radius: 3.0 m

DOCUMENTATION & TESTS INCLUDED

------------------------------

- Full GA drawings, cross-sections, BOM

- Material certificates (EN 10204 3.1 / 3.2)

- FAT reports including hydrostatic, fiber OTDR, electrical IR

- MRB, Coating report, Welding procedure qualifications

- Handling & Installation Manual (HIM)

- SDRL aligned with Equinor / NORSOK Z-001

SCHEDULE (high level)

---------------------

- Engineering & drawings approval: 12 weeks ARO

- Manufacturing & FAT: 34 weeks

- Delivery at Kristiansund Base: Week 42, 2026 (~11 months ARO)

ASSUMPTIONS & EXCLUSIONS

------------------------

- Offer assumes access to port/base, acceptance tests witnessed by DNV as specified.

- Excludes offshore installation, onshore installation services, customs clearance beyond DDP handover.

- Spare parts, additional preservations or expedited schedule priced separately.

- Supplier to provide production capacity schedule and detailed spool/reel plan prior to NTP.

CONTACT

-------

Aker Solutions - Commercial Contact (sample)

Email: sales@akersolutions.example

Phone: +47 70 00 00 00